## Slide 1: Project Management Workshop
Jordania leon-Jordan

## Slide 2: A project is…
A temporary one-time coordinated undertaking that:
has a goal/outcome;
has interrelated and dependent activities and tasks;
is finite in duration with starting and ending points;
uses resources: human, capital, systems;
produces unique product(s), service(s) or information;
operates under time, quality, cost, and scope targets / constraints

## Slide 3: Project Management Pitfalls
From the University of London Computer Centre Newsletter No.53, March 1973

## Slide 4: In simple terms…
Everyone wants a project to be…
          Good
          Fast
          Cheap

## Slide 5: The Magic is Balancing 4 key Elements
Quality
Cost
Time
Scope
Quality
Time
Cost
Scope

## Slide 6: In summary
Project Management is..
no more and no less than managing everything that needs to be done to finally hand over a specified deliverable to a customer in a way that satisfies the customers and key stakeholders.

## Slide 7: Project Management Framework
Leading and Managing
(Communications)
Conceptualization
(pre-project)
Initiation
Planning /
Scheduling
Executing /
Controlling
Closure
Project Phases

## Slide 8: Creating Questions
      Who?
        What?
          Where?
            When?
              Why?
                How?

## Slide 9: Project Management Framework
Leading and Managing
(Communications)
Conceptualization
(pre-project)
Initiation
Planning /
Scheduling
Executing /
Controlling
Closure
Project Phases

## Slide 10: Steps in Initiating the Project (I)
Understand the Project
  Review any relevant documents and gather information
Identify the Customers / Stakeholders
Develop a Business Case/Pre-Charter
Establish the Project Team
  Define roles and responsibilities
  Identify / select team members

## Slide 11: Steps in Initiating the Project (II)
Set Up the Project Management Processes
  Change Management, Risk Management, Issue Resolution, etc.
Draft the Project Charter
  Define the project strategy and approach
Schedule and Conduct a Kick-off Meeting
  Finalize the Project Charter
Establish the Communication Plan
  Who, what, when, and how of communicating

## Slide 12: Project Charter: Overview
What is it?
  Agreement between parties explaining how project will be managed and structured
  Collection of information the team needs to perform its day-to-day activities; defines the basic approach or process to be taken
  Documents processes that have been defined---a record of the work completed
  A living, breathing document

## Slide 13: Project Charter
Menu of Charter Elements
Project title
Project description
Business case
Stakeholders
Scope/Not-in-Scope
Deliverables
Implementation plan
Team members, roles
Approvals/sign-off
Budget/Resources
Project risks
Communication plan
Issue resolution plan
Change management plan
Process flow charts
Work Breakdown Structure

## Slide 14: Approval/Signoff
Approval / Signoff Process
  Executive sponsor should provide approval and signoff on the charter
  Every project has deliverables that may need to be approved before moving ahead

## Slide 15: Communication is Critical
Essential function that can dramatically affect the outcome of a project
Planning up front is worth its weight in gold
  Helps set priorities
  Ensures those who need information get it
  Avoids surprises
Plan should define who is responsible for what, where, when and how

## Slide 16: Communication Plan Checklist
Define the scope, deliverables and responsibilities
Identify the audience
Establish the communication goals
Determine the strategy for messages
Develop tools and opportunities
Establish milestones
Outline communication timeline and activities

## Slide 17: Communication Plan Elements
    Timing / calendar
    Message(s)
    Audience(s)
    Vehicle(s)
    Responsibility

## Slide 18: Project Management Framework
Leading and Managing
(Communications)
Conceptualization
(pre-project)
Initiation
Planning /
Scheduling
Executing /
Controlling
Closure
Project Phases

## Slide 19: Planning? Scheduling? Estimating?
What is Planning?
  Planning is the systematic identification and arrangement of tasks or steps to accomplish an objective
What is Scheduling?
  Scheduling is the process to define when each step will be done, how long will it take, and who will do it.
What is Estimating?
  Estimating is the process to determining how long each of the steps in the plan will take, how much each step is expected to cost, and when the steps will be completed.

## Slide 20: A Plan…
Demonstrates understanding (or not)
Is a roadmap to follow
Is a baseline to compare progress
Is a communication tool
Is a commitment to deliver
Provides information for the future projects

## Slide 21: How Do we Plan?
Start with the project objectives
What does “DONE” look like?
Define the tasks that need to get done.
Determine the sequence/relationships of those tasks.
Estimate the effort and duration of each task.
Assign responsibility for each of the tasks.
Document the schedule.
Affirm commitment from everyone
Set the project base-line.
Publish the plan.
Maintain the plan.

## Slide 22: Defining the Tasks
  Work Breakdown Structure (WBS)
    Plan the tasks
    Display levels of detail
    Communicate
    Defines the effort
    Used to build the schedule
  Input to WBS is the requirements defined in the project charter

## Slide 23: Example: Landscaping Project Tasks
Complete the landscape design
Install new fence
Remove trees and shrubs
Install sprinkler system
Remove old walkway
Install new walkways
Plant new shrubs and trees
Install new lighting
Plant new lawn
Call Digger’s Hotline

## Slide 24: WBS – Grouping Tasks
Complete the landscape design
Demolition
  Call Digger’s Hotline
  Remove trees & shrubs
  Remove old walkway
  Remove lawn as needed
Site Preparation
  Regrade soil
  Sprinkler piping
  Lighting rough-in
Finish Work
  Install fence
  Install walkway
  Plant shrubs
  Install sprinklers
  Install lighting

## Slide 25: Before Creating the Schedule
Questions while scheduling.
    Which tasks go first? And later?
    Which tasks can happen at the same time?
    Is there any “empty/slack” time?
    What are the relationships between tasks?
    What are the inputs to each task?
    What are the outputs to each task? (deliverables)
    Who will do each task?

## Slide 26: Example of Task Relationships
Landscape Project
Complete Design
Begin demolition
Call Digger’s Hotline
Remove trees and shrubs
Remove Walkway
Regrade Soil
Begin Site Prep
Remove Sod
Rough-in sprinklers
Rough-in lighting
Prep Walkway
Prep fence line
Finish sprinklers
Finish lighting
Install pavers
Install fencing

## Slide 27: The Planning Process
Start with a list of tasks
Determine logical dependencies among tasks
Identify skills needed to complete tasks
Assign resources to each task
Develop timeline for each task
Go back to point 1 until everything is complete

## Slide 28: The Scheduling Process
Start with a list of tasks
Organized tasks in “logical” order
Analyze the skills needed to do the work
Identify appropriate resources
Assign each task to people
Find the relationships between the tasks
Level the resources, if necessary

## Slide 29: Planning, Scheduling, & Estimating
Enter the tasks
Create the WBS
Identify predecessors/relationships
Enter the durations for each task
Assign resources for each task

## Slide 30: Project Management Framework
Leading and Managing
(Communications)
Conceptualization
(pre-project)
Initiation
Planning /
Scheduling
Executing /
Controlling
Closure
Project Phases

## Slide 31: Key Topics in Executive/Controlling
Risk Management
Change Management
Status and Progress Reporting
Control Tools

## Slide 32: What is Risk Management?
A systematic process of planning, identifying, assessing and handling project risks.

## Slide 33: Risk Management
Risk Management Process
    What’s a risk?
      An issue that hasn’t occurred yet, but could impact the project (positively or negatively)
    Why identify / mitigate risks?
      Naming a risk helps you identify what could happen
      Understanding a risk helps you determine mitigation strategies

## Slide 34: Identifying Risks
Risk Management Process
  Need to define
    Different levels of risks (high/medium/low)
    Probability/Impact/Severity of risks
    How risks are tracked
    Who is responsible for monitoring each risk
    What’s the plan for each risk
    How is it known that the “danger” is gone

## Slide 35: Risk Assessment/ Mitigation Template
Initial Risk Assessment
Risk Description | Probability (High, Med. Low) | Impact (High, Med. Low) | When Risk May Occur | Mitigation Plan
Team not able to clearly articulate business needs | Low | High | During Initiating/Planning Phase | Use a structured process for needs identification
Unavailability of key stakeholders and process owners | Medium | High | Anytime | Build relationships Pre-schedule time with stakeholders Identify and establish multiple communication channels

## Slide 36: Project Management Framework
Leading and Managing
(Communications)
Conceptualization
(pre-project)
Initiation
Planning /
Scheduling
Executing /
Controlling
Closure
Project Phases

## Slide 37: Why Is Project Closure Is Important?
To assess the project
To discuss lessons learned and best practices
So team feels a sense of completion and resources can be released for other projects
To provide recognition
To tie up loose ends
To transition to next effort

## Slide 38: Preparing for project closure
Establish and/or review transition plans to the operational owner and obtain approvals
Prepare signoffs for the key stakeholders
Complete administrative work
Gather project documents

## Slide 39: Project closure steps
Gather project feedback (surveys, etc.)
Prepare project closeout report
Have a Closeout Meeting
Complete the project, obtain signoffs, and transition to the operational owner
Recognize and reward the team-celebrate!